## 13-19 June
NO | ACTIVITIES | STATUS | COMMENTS
1 | Data Extraction for KPMG Data Review (Source & Staging) | Completed | Target Data Extract for KPMG upload is still pending. This activity is dependent on MOCK 3 Data Load
2 | Mock 3 Data Load (STATIC) | In progress | 1. CIF Load Completed 2. Signature, Pictures & Mandates Completed 2. CASA Account Completed 3. Amount Block Completed 4. Cheque Book - Not Completed 5. Cheque Details - Not Completed 6. Stop payments - Not Completed 7. Finanicial Data Upload - Not Started
3 | Production Storage Provision (Tablespaces) | Completed | This acitivity was as a request from FASYL to provision tablespaces for the Production environment. Six (6) tablespaces with varying sizes was provisioned
4 | Production Database Table Partitioning | Completed
5 | Tablespaces Error Resolution | Completed | This activity was as a result of an issue in deployment of war files by Dashan (FASYL)
6 | Script development for Special Interest Rate (Amplitude) | In progress
7 | Data Extraction for Special Interest Rate (Amplitude) | Not Started
8 | Script development and Data Extraction for Special Interest Rate (CWNet) | Completed
9 | Script development for ATM Card extraction | In progress

## 20-24 June
NO | ACTIVITIES | STATUS | COMMENTS
1 | Mock 3 Data Load (STATIC) | Completed | 1. Cheque Book - Completed 2. Cheque Details - Completed 3. Stop payments - Completed
2 | Mock 3 Data Load (FINANCIAL) | Completed | 1. CASA Account balance 2. GL Balance 3. Corporate Deposit 4. Standing Instructions (27 records could not be loaded due to some exceptions which are undergoing analysis)
3 | Data Extraction for KPMG Data Review (Target) | Completed | 1. Cheque Book - Completed 2. Cheque Details - Completed 3. Stop payments - Completed 4. CASA Account balance 5. Corporate Deposit 6. Standing Instructions
4 | Database Tablespace Extension (FC1405_DATAMED) | Completed | There was a need to increased the tablespace due to an on-going data import which exhausted the tablespace
5 | Archive Log size increased from 100G to 500G | Completed
6 | Archive Log size increased from 500G to 6TB | Completed
7 | Script development for Special Interest Rate (Amplitude) | In progress | The extraction scenario is a little complex making the script development a difficult one. In the interim, a decision was taken by the team lead (Prince Nitan) to manually book special interest for affected accounts for the purpose of UAT3

## 27-30 June
NO | ACTIVITIES | STATUS | COMMENTS
1 | Extraction of NOSTRO Accounts for Accounts Upload | Completed | 1. Nostro Customer Accounts which were not migrated due to their account nature was handled through a different extraction procedure for onward upload. Their balances was migrated into a TAKEDOWN account and will be uploaded using the DE module in FCUBS 2. This activity took us 4 working days to complete due to the exceptions and load challenges encountered
2 | OFSAA Data Mapping | Not Started
3 | Script development for Special Interest Rate (Amplitude) | In progress | The development of this script is becoming challenging for FINETECH. They have not been able to deliver on the request since 19th June, 2022

## 04-08 July
NO | ACTIVITIES | STATUS | COMMENTS
1 | Request for Swift Directory in Amplitude | Completed | An extract of all swift bank details was done from Amplitude for the purpose of data upload in FCUBS
2 | OFSAA Data Mapping | Not Started | Instructions have been given to me by my Team Lead to halt the data mapping exercise due to a misunderstanding between FASYL and the bank in relation to the primary responsible person for this task. The issue has been escalated to ED
3 | End of Day Run for UAT 3 | In progress (Continous process) | EOD run was completed with numerous issue resolutions. Duration for EOD is too lengthy. ( About 20 hours)
4 | Upload of SI's that failed Data Load | Partially completed | 2 SI's are still remaining to be uploaded. Exceptions issues are being analysed
h

## 11-17 July
NO | ACTIVITIES | STATUS | COMMENTS
1 | XNETT CTS, ACH Database Issue | Completed | A service connection issue to the XNETT Database was resolved
2 | OFSAA Data Mapping | In progress (Continous process) | ALM Data Mapping exercise started. The table STG_CASA which contains about 400 fields is being mapped. 10 fields has already been mapped
3 | End of Month Run for UAT 3 | In progress (Continous process) | EOM run was completed with few issue resolutions. Duration for EOM has significantly improved ( about 2 hours 40 mins)
4 | Creation of READ-ONLY Access user for Customized report | Completed | A read-only access user (report_user) was created for the purpose of development of Customized Reports

## 18-24 July
NO | ACTIVITIES | STATUS | COMMENTS
1 | Data Review with KPMG | Completed | A review exercise was conducted by KPMG to review the UAT3 data load exceptions
2 | Increment of FCUBS tablespace (FC1405_DATAMED) | Completed | Tablespace was increased by 100 GB
3 | End of Day Run for UAT3 | In progress (Continous process)
4 | OFSAA Data Mapping | In progress (Continous process) | 10 fields mapped for STG_CASA

## 25-31 July
NO | ACTIVITIES | STATUS | COMMENTS
1 | End of Day Run for UAT3 | In progress (Continous process)
2 | OFSAA Data Mapping | In progress (Continous process) | 22 fields mapped for STG_CASA (Team Lead has instructed me to halt the mapping exercise again)

## 01-07 Aug
NO | ACTIVITIES | STATUS | COMMENTS
1 | Customer Location Data Cleansing | Completed | A patch script was developed to update the migrated customer location
2 | EOD Group Allocation
3 | DE-Upload for UAT3 Issue fix
4 | Invalid UDF values resolution | Completed

## 08- Aug
NO | ACTIVITIES | STATUS | COMMENTS
1 | OBDX Database Directory creation | Completed | A database directory creation was requested by the FASYL team. This was created on a shared storage
2 | OBDX Schema and Tablespace creation on Production |  | The creation of the schema and tablespace was in done in preparation of Migrating OBDX on UAT2 environment to ODBX Production
3 | Customer Location Data Cleansing | Completed | Data cleansing of Customer Location was done using a developed script
4 | Invalid UDF values resolution | Completed | Identity card captured in the UDF field contained some invalid data which was corrected
5 | Fixed Asset Data Migration | On-going | A total of 7234 fixed asset record has been migrated. 38 records with exception could not load due to a location code '106' not maintained in FCUBS
6 | MOCK 4 Data Migration | On-going | Preparation for MOCK 4 Data Migration is underway.
7 | EOD Run on UAT 2 Environment | Completed | EOD run on UAT2 was specially requested
8 | UAT2 OBDX Data Import into PROD | Completed