## Project Handover Plan
PROJECT HANDOVER PLAN
CBA MIGRATION TO FLEXCUBE
| PLAN CREATED BY | DANIEL SAM-EGBEDE
| DATE | 2022-08-24
TASKS
No | TASKS | TRAINEE | DELIVERY MODE | START DATE | END DATE | NOTES
1 | Transfer of Migration Documents a. Explain each migration document structure b. Use cases for each document | TBD | 1. Documents will be shared through the Banks Network shared folder. 2. Explanation and use cases will be delivered in person (Instructor-Led) | 29-Aug, 2022 | 1-Sep, 2022
2 | Walkthrough for a typical Data Extraction Mock Run a. Data extraction and transformation b. Data validation c. Data exception handling d. Data extraction for review by KPMG | TBD | 1. Demo (In-person) Instructor-Led | 29-Aug, 2022 | 1-Sep, 2022
3 | Escalation Handling a. Modification of Data Extraction scripts b. Request for New extraction data sets c. Migration decisions | TBD | 1. Contacts details to be shared. 2. All handy documents (data dictionary etc) to be shared | 29-Aug, 2022 | 1-Sep, 2022
4 | EOD Activity a. Typical EOD run b. Reports extraction in EOD | TBD | 1. Demo (In-person) Instructor-Led | 29-Aug, 2022 | 1-Sep, 2022
5 | Miscellaneous Project task a. All DBA activities in relation to the CBA project b. Data Migration Weekly Reports c. Update status meetings | TBD | 1. Updates will be given (In-person) | 29-Aug, 2022 | 1-Sep, 2022
OUTSTANDING
1 | Extraction scripts to be completed. a. ATM extraction script b. Special interest extraction | TBD | 1. Review of scripts (In-person) Instructor-Led 2. based tables for special interest will be given | 29-Aug, 2022 | 1-Sep, 2022 | 1. I encountered a challenge extracting the special interest rate. So a decision was taken by the team lead for it to be booked manually.
2 | EOD group allocations | TBD | 1. Update will be given (In-person) | 29-Aug, 2022 | 1-Sep, 2022
3 | DE-Upload for UAT3 Issue fix | TBD | 1. Update will be given (In-person) | 29-Aug, 2022 | 1-Sep, 2022 | There is an issue relating to DE-Upload in FCUBS which needs to be analysed by both Fasyl and the bank for a possible resolution
4 | New table extraction for Frozen customers | TBD | 1. Update will be given (In-person) | 29-Aug, 2022 | 1-Sep, 2022 | There is a need to develop an extraction script for new data sets in relation to frozen customers
PENDING TRAINING
1 | EOD issues resolution | TBD | 1. Update will be given (In-person) | 29-Aug, 2022 | 1-Sep, 2022
2 | EOD reports generation | TBD | 1. Update will be given (In-person) | 29-Aug, 2022 | 1-Sep, 2022